## Backlog
Story ID | As a/an | Story | priority | addad in sprint | story point
1 | Quanlity Assurance Manager | I want to See the list of Most Popular ideas | must have | Sprint 1 |  |  | Technical
2 |  | I want to See the list of Most Viewed ideas | must have | Sprint 1 |  |  | Back-end | .NET core
3 |  | I want to See the list of Most Lastest Ideas | must have | Sprint 1 |  |  | Front-end | Html ,css , javascript, boostrap
4 |  | I want to CRUD categories | must have | Sprint 1 |  |  | Database | SQL server
5 |  | I want to View dashboard such as number of ideas per dep/year | must have | Sprint 2 |  |  | Server | Azure cloud
6 |  | I want to View dashboard such as number of contributor per dep | must have | Sprint 2
7 |  | I want to Download all idea data after the final closure date in CSV file | should have | Sprint 3 |  | Role | Task | Member
8 |  | I want to Download all uploaded documents in ZIP fomat | should have | Sprint 3 |  | Product owner | Evaluate requirement, make a plan | Tuan Anh
9 | Quanlity Assurence Coordinator | I want to Receive email notifications for new submissions from staff | should have | Sprint 3 |  | Interface design | Design Interface | Quoc Thai, Dang Khoa
10 |  | I want to See the lists of Most Popular Ideas | must have | Sprint 1 |  | Tester | Test | Vu Thai, Tuan Anh
11 |  | I want to see the lists of Most Viewed Ideas | must have | Sprint 1 |  | Scrum master | Track project progress, Division of work. | Lecturer Ban
12 |  | I want to See the list of Lastest Ideas | must have | Sprint 1 |  | Developer | Front-end | Quoc Thai, Dang Khoa
13 |  | I want to See the list of Lastest Comments | must have | Sprint 1 |  |  | Back-end | Vu Thai, Tuan Anh
14 | Staff | I want to Submit(upload) documents | must have | Sprint 1
15 |  | I want to Must agree to Terms and Conditions before they can submit documents | must have | Sprint 2 |  | Link Github | https://github.com/PeLaiahT/WebEnterprise
16 |  | I want to Can see all submitted ideas (not only their own ideas) | must have | Sprint 1
17 |  | I want to Can read comment for any other ideas | must have | Sprint 1
18 |  | I want to Can give comment for any other ideas until the final closure date | must have | Sprint 2
19 |  | I want to Can give Thumbs Up (Like) or Thumbs Down (Dislike) for any idea | should have | Sprint 3
20 |  | I want to Receive email notification when their ideas got new comment | should have | Sprint 3
21 |  | I want to See the list of Most Popular ideas | must have | Sprint 1
22 |  | I want to See the lists of Most Viewed Ideas | must have | Sprint 1
23 |  | I want to See the list of Lastest Comments | must have | Sprint 1
24 |  | I want to See the list of Lastest Ideas | must have | Sprint 1
25 | Admin | I want to Create new accounts Staff | Must have | Sprint 2
26 |  | I want to Create new accounts QA manager | Must have | Sprint 2
27 |  | I want to Create new accounts QA coordinator | Must have | Sprint 2
28 |  | I want to Set first closure date | Must have | Sprint 2
29 |  | Set final closure date | Must have | Sprint 2
30 |  | I want to Edit first closure date | Must have | Sprint 2
31 |  | I want to Edit final closure date | Must have | Sprint 2
32 |  | I want to Maintain system data: first closure date | Must have | Sprint 3
33 |  | I want to Maintain system data: final closure date | Must have | Sprint 3
34 |  | I want to See the lists of Most Popular Ideas | Should have | Sprint 1
35 |  | I want to See the lists of Most Viewed Ideas | Should have | Sprint 1
36 |  | I want to See the list of Lastest Comments | Should have | Sprint 1
37 |  | I want to See the list of Lastest Ideas | Should have | Sprint 1

## Sprint1
Task Name | Member | Estimate Time | Day1 | Day2 | Day3 | Day 4 | Day 5 | Day 6 | Day 7 | Status
CRUD Idea | Vu Thai, Tuan Anh | 8 | 2 | 2 | 2 |  | 2 |  |  | Finish
CRUD Category | Vu Thai, Tuan Anh | 4 | 2 | 2 | [5 empty] | Finish
Submit(upload) documents | Vu Thai, Tuan Anh | 3 | 1 | 1 |  | 1 |  |  |  | Finish
Create interface idea | Khoa, Quoc Thai | 3 | 2 | 1 | [5 empty] | Finish
Create interface category | Khoa, Quoc Thai | 4 | 2 | 1 |  | 1 |  |  |  | Finish
Create + Design DB | Vu Thai, Tuan Anh | 3 | 2 | 1 | [5 empty] | Finish
Code CRUD accounts (QA manager, QA coordinator, Staff) | Vu Thai, Tuan Anh | 4 | 2 | 2 | [5 empty] | Finish
Interface CRUD accounts | Khoa, Quoc Thai | 4 | 1 | 1 |  | 1 |  |  |  | Finish
Download documment | Vu Thai, Tuan Anh | 4 |  |  |  | 2 | 2 |  |  | Not Finish
Remaining effort | Daily Progress | 37 | 23 | 12 | 10 | 5 | 1 | 1 | 0
Ideal trend | Ideal Progress | 37 | 31.7143 | 26.4286 | 21.1429 | 15.8571 | 10.5714 | 5.2857 | 0

## Sprint2
2022-11-03
Task Name | Member | Estimate Time | Day1 | Day2 | Day3 | Day 4 | Day 5 | Day 6 | Day 7 | Status
Create Department | Vu Thai , Tuan Anh | 2 |  |  | 2 |  |  |  |  | Finish
Code login | Vũ Thai , Tuan Anh | 4 | 2 | 1 | 1 |  |  |  |  | Finish
Fix Upload File,Document | Vũ Thai , Tuan Anh | 4 |  | 2 | 2 |  |  |  |  | Finish
Download Document | Vũ Thai , Tuan Anh | 3 | 2 | 1 | [5 empty] | Finish
Add Image for User | Vu Thai , Tuan Anh | 4 |  | 1 | 2 | 1 |  |  |  | Finish
Fix Idea Controller | Vu Thai , Tuan Anh | 6 |  | 1 | 2 | 2 | 1 |  |  | Finish
Add Like Function | Vu Thai , Tuan Anh | 3 |  |  |  |  | 1 | 2 |  | Not Finish
Fix interface | Khoa, Quoc Thai | 8 | 3 | 3 | 2 |  |  |  |  | Finish
Add interface department(CRUD) | Khoa, Quoc Thai | 2 | 1 | 1 | [5 empty] | Finish
Add form login, logout | Khoa, Quoc Thai | 2 | 1 | 1 | [5 empty] | Finish
Remaining effort | Daily Progress | 38 | 29 | 18 | 7 | 4 | 2 | 0 | 0
Ideal trend | Ideal Progress | 38 | 32.5714 | 27.1429 | 21.7143 | 16.2857 | 10.8571 | 5.4286 | 0
Task Name | Members | Estimate Time | Day1 | Day2 | Day3 | Day 4 | Day 5 | Day 6 | Day 7 | Status
Code Download File | Tuan Anh | 3 | 1 | 1 | 1 |  |  |  |  | Finish
Code Comment | Vu Thai | 6 |  | 2 | 2 | 2 |  |  |  | Finish
Code Like && DisLike | Vu Thai | 6 | 2 | 2 |  | 2 |  |  |  | Finish
Set ClousureDate | Tuan Anh | 4 | 2 | 1 |  | 1 |  |  |  | Finish
Edit ClousureDate , FirstDate , LastDate | Tuan Anh | 4 |  |  | 1 | 1 | 2 |  |  | Finish
Interface Of Coment | Dang Khoa , Quoc Thai | 4 | 2 | 2 | [5 empty] | Finish
Interface Of Detail Coment | Dang Khoa , Quoc Thai | 6 |  | 2 |  | 2 | 2 |  |  | Finish
Interface of Set ClosureDate | Dang Khoa , Quoc Thai | 2 |  |  |  |  | 2 |  |  | Finish
Interface of Edit ClosureDate | Dang Khoa , Quoc Thai | 4 |  |  | 2 | 2 |  |  |  | Finish
Remaining effort | Daily Process | 39 | 32 | 22 | 16 | 6 | 0 | 0 | 0
Ideal trend | Ideal Process | 39 | 33.4286 | 27.8571 | 22.2857 | 16.7143 | 11.1429 | 5.5714 | 0